## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Overview of the project(MediTrain AI - Empowering the Doctors of Tomorrow, Today | MUST HAVE | NoDependencies | Mentor-506 | 3- Completed
S1 | S1 | US-002 | Workflow creation and project goal document | MUST HAVE | Charts | Mentor-506 | 3- Completed
S2 | S2 | US-003 | Document discussion(Agile Template,Defect Tracker,Unit Testing) | MUST HAVE | Excel sheets | Mentor-506 | 3- Completed
S2 | S2 | US-004 | Use Case Research and Preparation | SHOULD HAVE | W3 Schools and Docs | Mentor-506 | 3- Completed
S3 | S3 | US-005 | Python practice kit completion | MUST HAVE | Hacker Rank | Mentor-506 | 3- Completed
S4 | S4 | US-006 | Langchain,Flask, Prompts kit completion | MUST HAVE | Documentations | Mentor-506 | 3- Completed
S5 | S5 | US-007 | Project Discussion Module 1(Language Processing) | MUST HAVE | Groq API | Mentor-506 | 3- Completed
S6 | S6 | US-008 | Project Discussion Module 2(Workflow Efficiency) | SHOULD HAVE | VS Code | Mentor-506 | 3- Completed
S7 | S7 | US-009 | Project Discussion Module 3(Merging Existing Services) | SHOULD HAVE | Langchain | Mentor-506 | 3- Completed
S8 | S8 | US-010 | Project Discussion Module 4(Testing and Deployment) | COULD HAVE | Render | Mentor-506 | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 68 | 10 | 10 | 8 | 6 | 8 | 5 | 6 | 6 | 5 | 1 | 2 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-1 | TID-1 | Overview of the project(Chatbot for personalized learning) | 2024-11-04 | 2024-11-06 |  | Others | 3-Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-2 | TID-2 | Design the workflow and project goals | 2024-11-07 | 2024-11-08 |  | Design | 3-Completed | 4 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-3 | TID-3 | Exploring Documents(Agile Template,Defect Tracker,Unit Testing) | 2024-11-11 | 2024-11-11 |  | Others | 3-Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-4 | TID-4 | Reseach and preparation of the usecase | 2024-11-12 | 2024-11-14 |  | Others | 3-Completed | 4 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-5 | TID-5 | Finish the python practice set | 2024-11-16 | 2024-11-18 |  | Coding | 3-Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-6 | TID-6 | Completomg the rasa practice set | 2024-11-23 | 2024-11-27 |  | Coding | 3-Completed | 7 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-7 | TID-7 | Module 1 Discussion(Intent Recognition and Language Processing) | 2024-12-02 | 2024-12-05 |  | Build | 3-Completed | 12 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0
US-8 | TID-8 | Module 2 Discussion(Work Efficiency and Automation) | 2024-12-09 | 2024-12-14 |  | Coding | 3-Completed | 8 | 2 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-9 | TID-9 | Module 3 Discusssion(Merging with existing services) | 2024-12-15 | 2024-12-21 |  | Integration Test | 3-Completed | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
US-10 | TID-10 | Module 4(Verification and Deployment) | 2024-12-23 | 2024-12-26 |  | System Test | 3-Completed | 14 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 0 | 2 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 2 | Day 7 | Ambiguous User Stories | Conducted a story grooming session
Sprint 3 | Day 13 | Difficulty in solving problems | Collaborated with mentor when struck
Sprint 6 | Day 29 | Agile Template Confusion | conducted a meeting where all doubts were clear by the mentor
Sprint 7 | Day 34 | Confusion in integration of LMS | consulted with mentor to resolve the issue

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 3 | 2024-11-15 | 2024-11-22 |  |  | Delaying review of tasks | Maintaining focus on tasks | Achieved python kit completion on time
2 | Sprint 7 | 2024-12-15 | 2024-12-20 |  |  | using paid API'S | Exploring different LLM'S | Found a LLM that will be great for the chatbot
3
4
5
6
7